## Tasks and Timeline
Sauce & Spoon Project Plan
WBS # | Task | Owner | Start Date | Due Date | Duration | Notes | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Research data points on reservation systems and enhancement | Peta | 2021-05-08 | 2021-05-15 | 7
1.1.1 | Gather historical data on booking process | Peta | 2021-05-15 | 2021-05-15 | 0
1.2 | Align and evaluate stakeholders | Seydou | 2021-05-15 | 2021-05-17 | 2
1.3 | Calculate projections and enhancements | Peta | 2021-05-17 | 2021-05-25 | 8
1.4 | Interview members of the staff | Seydou | 2021-05-25 | 2021-05-19 | 6
1.4 | Create project charter (scope and goals) | Peta | 2021-05-26 | 2021-05-27 | 1
1.5 | Schedule kick off meeting | Peta | 2021-05-27 | 2021-05-27 | 0
2 | Sourcing
2.1 | Research reservation system options | Peta | 2021-06-06 | 2021-06-06 | 0
2.2 | Generate quotes and review costs | Deanna | 2021-06-05 | 2021-06-05 | 0
2.3 | Test out reservation systems | General Managers | 2021-06-05 | 2021-06-09 | 4
2.4 | Choose a reservation system | Peta | 2021-06-05 | 2021-06-09 | 4
2.5 | Vendor timeline and deliverables schedule | Peta | 2021-06-06 | 2021-06-10 | 4
3 | Planning
3.1 | Create contracts and statements of work for vendors | Peta | 2021-06-16 | 2021-06-15 | 1
3.2.1 | Message about launch date to stakeholders | Seydou | 2021-06-13 | 2021-06-13 | 0
3.3 | Project Plan Updates | Peta | 2021-06-15 | 2021-06-16 | 1
3.3.1 | Menu items information upload | General Managers | 2021-06-15 | 2021-06-17 | 2
3.3.2 | Coupon information upload | General Managers | 2021-06-16 | 2021-06-17 | 1
3.4 | Tablet Buy-in | Deanna | 2021-06-15 | 2021-06-17 | 2
3.4.1 | Source and hire electrician | Deanna | 2021-06-17 | 2021-06-19 | 2
3.5 | Place order for tablets | Seydou | 2021-06-14 | 2021-06-15 | 1
4 | Execution
4.0.1 | Shipping buffer for tablets | Seydou | 2021-06-15 | 2021-06-25 | 10
4.1 | Training of Managers | Seydou | 2021-06-16 | 2021-06-17 | 1
4.1.1 | Manager Training of Employees | General Managers | 2021-06-17 | 2021-06-20 | 3
4.2 | Wiring Tables | Sub-Contractor | 2021-06-13 | 2021-06-14 | 1
4.2.1 | Software Installation | Seydou | 2021-06-14 | 2021-06-17 | 3
4.3 | POS Integration | Peta | 2021-06-15 | 2021-06-28 | 13
5 | Acceptance Testing
5.1 | Tablet integration testing | Seydou | 2021-06-15 | 2021-06-22 | 7
5.2 | Tablet - kitchen integration check | Seydou | 2021-06-16 | 2021-06-17 | 1
5.3 | Friends and Family night | Deanna | 2021-06-17 | 2021-06-20 | 3
5.4 |  |  | 2021-06-13 | 2021-06-14 | 1
5.5 | New tablet install |  | 2021-06-15 | 2021-06-28 | 13

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Wiring tables | Electrician vendor needed | 4 | 2 | 4 | 6 | H
Branding | Branding package needed (through terriffic tablets) | 2 | 1 | 2 | 5 | L
Training | Key staff identification & implementation training needed | 5 | 1 | 5 | 8 | H
No Tip Function | Requires staff buy-in | 2 | 1 | 2 | 4 | L
Tablet buy-in | Staff input on change to produce sense of self-determination | 2 | 1 | 2 | 4 | M
Shipping buffer | About a week for delivery (low risk of stock outage) | 10 | 7 | 10 | 20 | M
Menu items information |  | 3 | 2 | 3 | 6 | H
Coupons information |  | 3 | 2 | 3 | 6 | H
POS integration | May need to update some locations to 3.0 for integration to be done in hours | 2 | 1 | 2 | 5 | L
Project plan updates |  | 4 | 2 | 4 | 6 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Importance of tech alignment | https://www.businessobserverfl.com/article/outback-co-founder-chris-sullivan-leadership-lessons-iconic-restaurant-chain |  | Opening without having tech perfect lead to negative cx exp and closed locations
Prevalence and control of bacteria on touchscreen devices | http://www.foodprotection.org/files/food-protection-trends/may-jun-20-jones.pdf |  | Establish cleaning schedule

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Faster, more efficient experince | Average ticket time |  | 8min Apps, 12-15min entrees | FALSE
| Table turn |  | 30 min | FALSE
| Checkout time |  | 1min | FALSE
Customer Satisfaction | Technical issues |  | <5% in first 6mo | FALSE
Incorrect Orders | Order Accuracy | - Are customers receiving the correct orders? - Since using the tablets, how often have you sent back an incorrect order? | 100% | FALSE
| Lobby Waittime |  | <10min | FALSE
Waitstaff Efficiency |  | On average, how many of your side work tasks are you able to complete during a shift? |  | FALSE
Customer Satisfaction |  | - Which customers are posting about their exp on social media? - Are customers having a better dining experience with the tablets? |  | FALSE
|  | Are tablets easy to use? |  | FALSE
|  | Was there enough time during the training to practice and ask questions? |  | FALSE
FALSE
|  | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience? |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Faster, more efficient experince | - Are customers receiving the correct orders? - Since using the tablets, how often have you sent back an incorrect order? | 8min Apps, 12-15min entrees | - Since using the tablets, how often have you sent back an incorrect order? | Open-ended | 1%+ | 5%+ | 20%+ | 50%+
|  |  | - Are customers receiving the correct orders? | Yes/No | Yes | No
| On average, how many of your side work tasks are you able to complete during a shift? | 1min | On average, how many of your side work tasks are you able to complete during a shift? | Open-ended | 1+ | 3+ | 5+ | 10+
Customer Satisfaction | - Which customers are posting about their exp on social media? - Are customers having a better dining experience with the tablets? | <5% in first 6mo | - Which customers are posting about their exp on social media? - Are customers having a better dining experience with the tablets? | Open-ended | Yes | No | 1+ Platform | 3+ Platforms
Incorrect Orders | Are tablets easy to use? | 100% | Are tablets easy to use? | Yes/No | Yes | No
| Was there enough time during the training to practice and ask questions? | <10min | Was there enough time during the training to practice and ask questions? | True/False | TRUE | FALSE
Waitstaff Efficiency |  | 30 min
Customer Satisfaction | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience? |  | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience? | Scaled | 1 | 2 | 3 | 4 | 5